## Projected Professional Fees
Item |  | Units | Unit cost
structural calcs/report | 1000 |  |  | 21647.01 | Up front costs (held back from initial payments)
architect | 6000
planning app | 4050 | 9 | 450
planning consultant | 2000
legals (exchange) | 2300
legals JV | 2500
tree survey | 0
VAT | 0
project manager | 30000 | 6 | 5000
asbestos survey | 600
building control | 1500
M&E calcs
SAP calcs/EPC | 360 | 9 | 40
Ventilation study | 500 |  | 500
Water calcs
warranties | 7200 | 9 | 800
QS internal | 0 | 2 | 0
QS Lender | 2000 | 3
Agents fees | 0
Valuation | 2400
broker fees | 0
arrangement fees | 0
legal indemnity (lender) | 0
drainage survey
noise consultant | 1500
marketing | 200
design & build contract | 200
insurance
CIL | 0
S106 | 1097.01
Agents fees (Exit) | 15000 |  | 1%
Lenders fee (Exit) | 0
Solicitors (Exit) | 5400 |  | 600
Show flat | 5000
Furniture for letting
90807.01

## Professional Fees Paid
Professional Fees
Month paid | Recipient | Item description | Amount paid
2019-11-01 | Rochaus | Architect's fees | 1152
2019-12-01 | Rochaus | Architect's fees | 4656
| Ipswich BC | Planning application fees | 4158
| Attwells Solicitors | Legal fees for exchange (aborted) | 2398.8
2020-01-01 | **** | **** | 0
2020-02-01 | **** | **** | 0
2020-03-01 | Doorsteps | Sales advertising | 94.05
2020-04-01 | **** | **** | 0
****
2020-05-01 | **** |  | 0
2020-06-01 | Ipswich BC | Building control fees | 696
| Robin Bryer | Planning consultant for application | 1800
| Robin Bryer | Site visit | 250
| Robin Bryer | Initial planning advice | 50
2020-07-01 | Ipswich BC | Building control fees | 50
2020-08-01 | **** | **** | 0
2020-09-01 | Thomspon Reuters | JCT D&B contract | 165.6
2020-10-01 | HJ Structural Engineers | Structural survey | 594
2020-11-01 | Aas | Asbestos survey | 720 | 13665.65 | 16784.45
2020-12-01 | Rochaus | Additional architecture fees required for BC | 4104
| Rochaus | Additional architecture fees for design changes | 1200
| Ipswich BC | Section 106 payment | 1097 |  |  | *Show flat allowance = £5,000
| Gain Consultants Ltd | Project management fees (Nov) | 5000 |  |  | total as at 1st Feb - | 310.72
| Gain Consultants Ltd | Project management fees (Dec) | 5000 | 16401 | 16401
2021-01-01 | Gain Consultants Ltd | Project management fees (Jan) | 5000
| Ipswich Borough Council | Building Control fees | 1680
| Hewitsons LLP | Legal fees for JV | 2064.6
| *Dusk | Show flat | 172.12
| Doorsteps | Sales re-advertising fees | 99
| *William Wood Design | Show flat | 138.6 | 9154.32 | 9154.32
2021-02-01 | Gain Consultants Ltd | Project management fees (Feb) | 5000
| eBay | Show flat items | 13.49
| eBay | Show flat items | 119.99
| eBay | show flat items | 135.24
| Promax Ltd | show flat items | 52.5
| Dongguanlew | show flat items | 16.99
| Liushujuan | show flat items | 6.97
| Mokeyundima | show flat items | 9.59
| Sarah Veraso | show flat items | 5.14
| ZZP | show flat items | 8.46
| eBay | show flat items | 69.95
| eBay | show flat items | 269
| eBay | show flat items | 16.99
| eBay | show flat items | 50
| ZZP | show flat items | 6.88
| eBay | show flat items | 12.59
| Wayfair | show flat items | 104.99
| TK Maxx | show flat items | 33.98
| eBay | show flat items | 465 |  |  | *Show flat allowance = £5,000
| eBay | show flat items | 139.99 |  |  | total as at 1st Mar - | 2042.21
| eBay | show flat items | 10.95
| 2umno7 | show flat items | 10
| Wordery | show flat items | 21.55
| UK Retrading | show flat items | 43.98
| Jingtingdia | show flat items | 15.94
| Klarna Desenio | show flat items | 91.33 | 6731.49 | 6731.49
2021-03-01 | 39 Essex Chambers | Counsel's advice on the Right of Way issue | 4200
| Gain Consultants Ltd | Project management fees | 5000
| Refund to Ricky Sharpe | show flat items | 50.99
| Refund to Ricky Sharpe | show flat items | 329.99 |  |  | *Show flat allowance = £5,000
| refund to Ricky Sharpe | show flat items | 249.5 |  |  | total as at 1st Apr (final cost) - | 5427.18
| Refund to Ricky Sharpe | show flat items | 26.55
| Refund to Ricky Sharpe | show flat items | 11.95
| Refund to Ricky Sharpe | show flat items | 329.03
| Refund to Ricky Sharpe | show flat items | 613.93
| Refund to Ricky Sharpe | show flat items | 773.03
| Georgina Sharpe | Interior Styling | 1000 | 12584.97 | 12584.97
2021-04-01 | Sedgwick International | lender's cost monitor | 1068
| Gain Consultants | project management fees | 5000 | 6068 | 6068
2021-05-01 | Gain Consultants | project management fees | 5000
| Colliers |  | 3300
| Colliers |  | 900
| Colliers |  | 900
| Colliers |  | 900 | 11000 | 11000
2021-06-01 | Gain Consultants | project management fees | 5000
| HJ structual engineer | Structual survey | 684 | 5684 | 5684
2021-07-01 | Gain Consultants | project management fees | 5000 |  | 5000
2021-08-01 | Gain Consultants | project management fees | 5000 |  | 5000
|  | Total | 94408.23

## Construction Fees Paid Direct
Construction Fees Paid Direct from SPML Museum Ltd
Month paid | Recipient | Item description | Amount paid | Total
2021-04-01 | Iron Glaze | Secondary glazing deposit | 5000
2021-05-01 | Granite supply Ltd | Granite work tops | 1890
| Granite supply Ltd | Granite work tops | 4320
| Soho Commerical Ltd | Bins | 824.4
7034.4
2021-06-01
2021-07-01 | Roofing superstore | Roofing supplies - vents etc | 2098.2
12th July 2021 | Discount Flooring | Flooring for Flats | 4331.7
13th July 2021 | Halfords | Bike Racks | 39.99
13th July 2021 | GardenChic | Bike Racks | 353
14th July 2021 | Ebay | Shower Trays | 78.09
14th July 2021 | Ebay | Toilets | 773.7
15th July 2021 | Ebay | Bathroom Cabinet | 140.39
15th July 2021 | Ebay | Ovens | 449.85
15th July 2021 | Ebay | flooring for Flats | 556.37
15th July 2021 | CPC | Items for Museum St | 221.68
16th july 2021 | Glo Tech | fridge freezers | 2190
19th July 2021 | Premier Farnell | lights | 226.02
11458.99
18.8.21 | Inta Audio | ceiling speakers | 191.91
18.8.22 | Ebay | ceiling speakers | 167.93
23.8.21 | ebay | underlay | 70.99
24.8.21 | Ebay | Kitchen taps | 132
26.8.21 | ebay | hobs x3 | 270
832.83
|  | Total | 24326.22

## Contractor Invoices
Sovereign Builders Invoices
Month 1 - Nov | 21491 | paid (2 parts) - 16th & 18th Dec
Month 2 - Dec | 21595 | paid (2 parts) - 14th & 19th Jan
Month 3 - Jan | 20920 | paid (2 parts) - 1st & 10th Feb
Month 4 - Feb | 20279 | paid (2 parts) - 1st & 12th Mar
Month 5 - Mar | 26903 | paid (3 parts) - 26th Mar, 12 & 13th Apr
Month 6 - April | 17064.85 | paid (2 parts) - 6th May. 27th May
Month 7 - May | 19606 | paid (2 parts) - 11th June and 24th June
Month 8 - June | 15972 | paid (2 parts) - 8th July and 23rd July
Month 9 - July | 3888 | paid (1 part) - 13th August
Month 10 - August
Total | 167718.85

## Drawdown Summary
Drawdown Summary
Museum Street | Costs removed from DA as pre-contract costs | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01
Drawdown Summary
Contractors Invoice |  | 21491 | 21595 | 20920 | 20279 | 26903 | 17064.85 | 19606 | 15972 | 3388 |  | 167218.85
Professional fees and Management chrges (Gain) | 21647 | 16784.45 | 16401 | 9154.32 | 6731.49 | 12584 | 6068 | 11000 | 1684 | 5000 | 5000 | 112054.26
Construction fees paid direct by SPML Museum Ltd |  | 2021-04-01: 5000; 2021-05-01: 6210; 2021-06-01: 684; 2021-07-01: 11458.99; 2021-08-01: 832.83 | 24185.82
Net amount of claim | 21647 | 38275.45 | 37996 | 30074.32 | 27010.49 | 39487 | 28132.85 | 36816 | 18340 | 19846.99 |  | 297626.1
Drawndown notice figure |  | 28029.43 | 26595 | 30074.32 | 27010.49 | 39487.97 | 28132.85 | 38540.4 | 21565 |  |  | 239435.46